## Project Planner
Software Engineering Practise
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Weekly Highlight: | 9 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete | Actual (beyond plan) | % Complete (beyond plan)
MISSION | MISSION START | MISSION DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEKS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Project management | 1 | 15 | 1 | 15 | 50%
Requirment analysis | 1 | 5 | 1 | 6 | 100%
Sofware analysis | 1 | 5 | 1 | 6 | 100%
Testing | 12 | 2 | 0 | 0 | 10%
Job progress compnent | 6 | 5 | 6 | 0 | 60%
Data Component | 6 | 5 | 6 | 0 | 85%
Task allocation component | 11 | 3 | 0 | 0 | 0%
User account component | 6 | 5 | 6 | 5 | 60%
Job delay component | 11 | 3 | 0 | 0 | 0%
Statistics component | 6 | 5 | 6 | 0 | 25%